

Contract Nb. 2020-1-FR01-KA202-080105 (2020-2023)

**Review and update of deadlines and outcomes to 7 July 2022**

|  |  |  |
| --- | --- | --- |
| Deadlines decided in Paris(12 May 2022) | Contents | Comments and adjustments |
| **Before 15 of June 2022** | **Object**: validation of the general model **FOR the preparation of trainers, monitors & company tutors who will be involved in the training of site managers and team leaders IN EACH PARTNER COUNTRY** proposed by Lukasiewicz**Partners concerned:** FORMEDIL (IT), PEDMEDE (GR), FLC Asturias (ES) | See this operational model on [https://www.renovup.org/wp-content/uploads/2022/05/00A.-RenovUp-4th-Transnational-Meeting-2022-05-11-12-Minutes.pdf - page 7](https://www.renovup.org/wp-content/uploads/2022/05/00A.-RenovUp-4th-Transnational-Meeting-2022-05-11-12-Minutes.pdf%20-%20page%207)The partners concerned (**Formedil, Pedmede & FLC Asturias**) are kindly asked to approve the operational training model or give their suggestions **before the end of July 2022**. After this new deadline, CCCA-BTP & Lukasiewicz will **consider that the model is adopted even if the explicit answer is not given.** |
| **End of June 2022** | **Object**: results of test Grids 1 & 2, with trainers specialised in the fields concerned**Partners in charge**: CCCA-BTP (FR) with BTP CFA Pays de la Loire (FR) | Task fulfilled as decided in Paris. The results are available on <https://www.renovup.org/wp-content/uploads/2022/07/01A.-Methodology-tested-in-France-to-observe-work-situations-on-renovation-sites-EN.docx> and <https://www.renovup.org/wp-content/uploads/2022/07/02A.-Observation-grids-tested-in-France-to-observe-work-situations-on-renovation-sites-EN.docx> |
| **End of June 2022** | **Object**: Open Badges, giving opinions and preferences**Partners concerned**: All | The CCAB intends to move forward with the preparation of the Open Badges, including new experts in this work. Thus, we need to know the preferences of the partners as to which option each prefers for Open Badge 2 (for trainees) - Variant 1 or Variant 2.After an initial exploration, Variant 2 seems to be a better fit. **However, the partners are invited to give their opinion before the end of July 2022.** The choice made by the majority of the partners will be respected. Therefore, it is ESSENTIAL to communicate your preference.Full document available on <https://www.renovup.org/wp-content/uploads/2022/05/07.-IO2-A2.-Open-Badges-pour-RenovUp-EN.docx> (especially Page 2)  |
| **End of June 2022** | **Object**: promotion, actions/events/publications**Partners concerned**: All | The list of dissemination & valorisation actions/events/publications – to be sent to CCCA-BTP (marion.beauchesne@ccca-btp.fr cc.marek.lawinski@ccca-btp.fr), initially for June 30th, 2022, **is now to be sent for August 31st, 2022**Link: <https://www.renovup.org/wp-content/uploads/2021/10/14.-RenovUp_Valorisation-Journal_-2021-12-21.xlsx> |
| **June/July 2022** | **Object**: testing Grids 1 & 2 in their contexts, with identified trainers on a building site**Partners in charge**: FORMEDIL (IT), PEDMEDE (GR), LUKASIEWICZ (PL), FLC Asturias (ES) | FLC Asturias has completed the work. **Congratulations 😊**! Results available on <https://www.renovup.org/wp-content/uploads/2022/07/01C.-Methodology-tested-in-Spain-to-observe-work-situations-on-renovation-sites-EN.docx> and <https://www.renovup.org/wp-content/uploads/2022/07/02C.-Observation-grids-tested-in-Spain-to-observe-work-situations-on-renovation-sites-EN.docx>Considering the complexity of this task, **all the other partners (Pedmede, Formedil & Lukasiewicz) have until September 15th 2022 to test Grids 1 & 2.** They can draw on the experiences made by the CCCA-BTP and the FLC Asturias. |
| **End of July 2022** | **Object**: collecting results and publishing the updated version of all the grids after the testing by the partners**Partners in charge**: CCCA-BTP (FR) | Considering the previous adjustments, **the new deadline is September 30, 2022**. |
| **End of September 2022** | **Object**: Clarifying on how to transform observations made in the workplaces into training objectives**Partners in charge**: CCCA-BTP (FR), FLC Asturias (ES) | No change. |
| **Mid October 2022** | **Object**: finalisation of the trainer/teacher preparation scheme**Partners in charge**: LUKASIEWICZ (PL), CCCA-BTP | No change. |
| **Mid October 2022** | **Object**: identification of teachers/trainers for the experimental preparation session**Partners concerned**: All | No change. |
| **End of October 2022** | **Object**: starting of experimental preparation of teachers/learners**Partners concerned**: All | No change. |
| **3rd week of November 2022** | **Object**: 5th transnational meeting in Rome (instead of Athens originally planned in October)**Partners concerned**: All | Rome 22 (9am-6pm) & 23 (9am-1pm) November 2022Hosting Partner: Formedil |